## Love
Front End |  |  |  |  | Back End |  | Other
Item | Wireframes | Mockups | Development | Subtotal | Item | Hours | Item | Hours
Navigation | 3 | 8 |  | 11 | Authentication | 15 | Data import scripts | 28
Brand |  | 25 |  | 25 | Users | 12 | Project management | 27.72
Website |  | 5 | 20 | 25 | Blueprint | 6 | Ongoing development | 40
Sandbox |  |  | 20 | 20 | Facilities | 15 | Buffer | 10%
Authentication | 1 | 3 | 5 | 9 | Spaces | 12 | Back end total | 105.292
Budget | 10 | 10 | 40 | 60 | Line Items | 18 | Cost | 12635.04
Quick add item | 8 | 5 | 5 | 18 | Schedule | 6
Walkthrough | 8 | 10 | 15 | 33 | Budget | 20
Add item | 2 | 5 | 2 | 9 | Budget - creation | 6
Space list view | 3 | 3 | 2 | 8 | Budget - export to PDF
Account | 1 | 1 | 3 | 5 | Budget - statuses | 3
Spaces | 1 | 3 | 3 | 7 | Documentation | 10
Facilities | 8 | 4 | 10 | 22 | Boilerplate | 25
|  |  | Buffer | 10% | Buffer | 10%
|  |  | Front end total | 277.2 | Back end total | 162.8
|  |  | Cost | 33264 | Cost | 19536
Total
Item | Hours
Front end | 277.2
Back end | 162.8
Etc | 105.292
Total | 545.292
Cost | 65435.04

## Want
Front End |  |  |  |  | Back End |  | Other
Item | Wireframes | Mockups | Development | Subtotal | Item | Hours | Item | Hours
Navigation | 3 | 5 |  | 8 | Authentication | 15 | Data import scripts | 28
Brand |  | 20 |  | 20 | Users | 12 | Project management | 0
Website |  | 10 |  | 10 | Blueprint | 6 | Ongoing development | 40
Sandbox |  |  | 20 | 20 | Facilities | 15 | Buffer | 8%
Authentication | 1 | 3 | 5 | 9 | Spaces | 12 | Back end total | 73.44
Budget | 10 | 10 | 40 | 60 | Line Items | 18 | Cost | 8812.8
Quick add item | 8 | 5 | 5 | 18 | Schedule | 6
Walkthrough | 8 | 10 | 10 | 28 | Budget | 20
Add item | 2 | 5 | 2 | 9 | Budget - creation | 6
Space list view | 3 | 3 | 2 | 8 | Budget - export to PDF
Account | 1 | 1 | 3 | 5 | Budget - statuses | 3
Spaces | 1 | 3 | 3 | 7 | Documentation | 10
Facilities | 6 | 4 | 10 | 20 | Boilerplate | 25
|  |  | Buffer | 8% | Buffer | 8%
|  |  | Front end total | 239.76 | Back end total | 159.84
|  |  | Cost | 28771.2 | Cost | 19180.8
Total
Item | Hours
Front end | 239.76
Back end | 159.84
Etc | 73.44
Total | 473.04
Cost | 56764.8

## Have to have
Front End |  |  |  |  | Back End |  | Other
Item | Wireframes | Mockups | Development | Subtotal | Item | Hours | Item | Hours
Navigation | 3 | 5 |  | 8 | Authentication | 15 | Data import scripts | 28
Brand |  | 20 |  | 20 | Users | 12 | Project management | 0
Website |  | 10 |  | 10 | Blueprint | 6 | Ongoing development | 0
Sandbox |  |  | 20 | 20 | Facilities | 15 | Buffer | 5%
Authentication | 1 | 3 | 5 | 9 | Spaces | 12 | Back end total | 29.4
Budget | 10 | 10 | 40 | 60 | Line Items | 18 | Cost | 3528
Quick add item | 8 | 5 | 5 | 18 | Schedule | 6
Walkthrough | 8 | 10 | 10 | 28 | Budget | 20
Add item | 2 | 5 | 2 | 9 | Budget - creation | 6
Space list view | 3 | 3 | 2 | 8 | Budget - export to PDF
Account | 1 | 1 | 3 | 5 | Budget - statuses | 3
Spaces | 1 | 3 | 3 | 7 | Documentation | 10
Facilities | 6 | 4 | 10 | 20 | Boilerplate | 25
|  |  | Buffer | 5% | Buffer | 5%
|  |  | Front end total | 233.1 | Back end total | 155.4
|  |  | Cost | 27972 | Cost | 18648
Total
Item | Hours
Front end | 233.1
Back end | 155.4
Etc | 29.4
Total | 417.9
Cost | 50148